## Environmental Assessment
Poject Coordination Point | HQ Task | Task Responsibility | Meeting Topics | Deliverable to HQ | Attendees | HQ Review Periods - Working days
OSMRE Decision to Prepare EA | Review and Maintain CEQ-OEPC Tracking Files | Region | N/A | Evaluation of Proposed action for NEPA Compliance Form (NEPA Form) | N/A | 2 days
OSMRE Internal “Kick-off” Meeting -Identify Start of Study (SOS) date | Review and provide Department updates | Region | Senstive Issues Data Colllection Status Agency Coordination Requests; Scoping/Public Satus Review Schedule | Meeting Agenda Draft Schedule List of data available | Regional Team Solicitors HQ Staff | Meeting held within 30-days after NEPA Form to HQ
OSMRE EA Development (as needed) | Review | Region | EA Outline, Data, Draft Analysis Methodologies, and schedule status | Agenda Annotated Outline | Regional Team Solicitors HQ Staff | 1 week
EA Check-in (project dependent) | Department Update | HQ and Region | EA Status and potential red flags | Briefing memo and Updated Schedule | Deputy Dir. | 5 days
Internal draft EA | Review | Region and HQ | N/A | draft EA, Appendices, and Schedule | N/A | 2 weeks
Solicitor Review | -- | Regional Solicitor (HQ as needed) | N/A | draft EA | N/A | 2 weeks
Director Briefing (project dependent) | Director Briefing Coordination | HQ | EA and Review Team Presentation | Project Summary, Draft EA, and presentation materials | Deputy Dir. | 1 week
Responses to EA Public Comments | Review | Region - Conference Call | Public Comments Draft Responses, and Schedule Update | Agenda; Draft response Schedule | Region PM; Solicitors and HQ Staff HQ Solicitor | 1 week
Internal draft Findings and decision document | Review draft findings and Decision document | Region and HQ | N/A | Draft Finding and Decision document | N/A | 2 weeks
Solicitor Review | --- | Regional Solicitor | N/A | Draft Final EIS | N/A | 2 weeks
Director Briefing (project dependent) | Director Briefing Coordination | HQ and Region | FEIS Findings and Review Team Presentation | Draft Department Review Team presentation and review materials | Deputy Dir. HQ Staff; OC Region Dir Region Team solicitor | 1 week
OMRE GUIDE - NEPA Review and Coordination Points
Environmental Assessment (EA)