## Kentucky
Kentucky
| Key | Awaiting action by the State
Under action by Department
ATP Issued
Project Complete
Fiscal Year 2022 Projects
Project Name | County(s) | Grant Funding | Status
CMH 23 Workforce & Tourism Development | Floyd | 1000000 | Under action by Department
Southeast Training Center | Knox | 1950000 | Under action by Department
Fiscal Year 2021 Projects
Project Name | County(s) | Grant Funding | Status
Apple Cold Storage | Martin | 2500000 | Under action by Department
Ashland Convention Center | Boyd | 1000000 | Awaiting action by the State
Highlands ARH Equipment | Floyd | 750000 | Awaiting action by the State
Leeco Campground | Leslie | 1000000 | Awaiting action by the State
Manchester Farm | Clay | 700000 | Under action by Department
Sag Hollow | Owsley | 600000 | Under action by Department
Whitesburg Agritech: High Tunnel to the Future | Clay | 1000000 | Awaiting action by the State
Wolfpit Technology and Industrial Park Phase II | Pike | 700000 | Awaiting action by the State
Fiscal Year 2020 Projects
Project Name | County(s) | Grant Funding | Status
Buckhorn WTP & 15- 7 Interconnect | Perry | 3500000 | Awaiting action by the State
BPM Lumber Value-Add | Laurel | 3769000 | Under action by Department.
EastPark Building for Project Jobs | Greenup / Boyd | 1500000 | Awaiting action by the State
Duvall Valley Area | Clinton | 3000000 | Under action by Department.
Harlan County Business Park Gas Infrastructure | Harlan | 1500000 | Awaiting action by the State
King's Daughters Health System Expansion | Boyd | 4000000 | ATP Issued
Lynch Motorsports Welcome Center | Harlan | 400000 | Awaiting action by the State
PMC Cancer Center Expansion | Pike | 4270000 | ATP Issued
Wheelwright Water System | Floyd | 2050000 | Awaiting action by the State
Fiscal Year 2019 Projects
Project Name | County(s) | Grant Funding | Status
Advanced Manufacturing and Construction Center | Perry | 2500000 | Awaiting action by the State
Drone Port Water and Sewer | Knott / Perry | 743000 | Awaiting action by the State
EKY Builds Pinnacle Park | Martin | 2000000 | Awaiting action by the State
International Landing Zone | Martin | 1370000 | Awaiting action by the State
Knott Count Water & Sewer District Generators | Knott | 600000 | Awaiting action by the State
Leslie County Connectivity & Teleworks | Leslie | 2056000 | Awaiting action by the State
Mine Made Adventures | Knott | 1706000 | ATP Issued
Paintsville Sewer Expansion | Johnson | 4000000 | Awaiting action by the State
PMC's Children's Hospital | Pike | 4780000 | Project Complete
South Fork Elk View Phase II | Breathitt | 1345000 | ATP Issued
Thunder Mountain Phase II | Letcher | 2400000 | Awaiting action by the State
Wayland to Lackey Waterline Replacement | Floyd | 1500000 | ATP Issued
Fiscal Year 2018 Projects
Project Name | County(s) | Grant Funding | Status
Beattyville Connect | Lee | 1250000 | ATP Issued
Big South Fork Scenic Railway Blue Heron Slide Repair | McCreary | 1500000 | Project Complete
Blue Heron Spur Slide Repair | McCreary | 334000 | Project Complete
eKAMI Prison Reform/Workforce Development | Morgan | 6400000 | Awaiting action by the State
Harlan County River Launches | Harlan | 376000 | Awaiting action by the State
Impact Outdoors Phase III | Clay | 350000 | ATP Issued
Kentucky Coal Heritage Trail | Floyd | 225000 | Awaiting action by the State
Martin Water System Improvements - Big Sandy | Martin | 2000000 | Awaiting action by the State
Outdoor Ventures Corporation Expansion Project | McCreary | 3500000 | ATP Issued
Project Core (Dajcor) | Perry | 6500000 | Project Complete
Thunder Mountain Phase I | Letcher | 1065000 | Awaiting action by the State
USA Drone Port | Perry / Knott | 1500000 | Awaiting action by the State
Fiscal Year 2017 Projects
Project Name | County(s) | Grant Funding | Status
Coalfields Regional Industrial Park Gas Supply | Perry | 900000 | Project Complete
EastPark Industrial Park Infrastructure and Development | Boyd / Greenup | 4000000 | Project Complete
eKAMI Phase II | Johnson | 1000000 | Project Complete
Federal Prison at Roxana Waste Water Treatment Plant | Letcher | 210000 | Awaiting action by the State
Federal Prison at Roxana Waterline Extensions | Letcher | 3800000 | Under action by Department
HCTC Lineman Training Expansion | Perry | 280000 | Awaiting action by the State
Historic Stearns Downtown Revitalization | McCreary | 1100000 | ATP Issued
Impact Outdoors Phase II | Clay | 200000 | Project Complete
KEIP Spec Building | Pike | 5710000 | Project Complete
Knott-Perry Route 80 & 476 Interconnect WSP | Perry / Knott | 1250000 | ATP Issued
Martin County Water Controls and Mods | Martin | 2250000 | ATP Issued
Rush Off Road | Boyd | 4000000 | Awaiting action by the State
Whitesburg Farmers Market Pavilion | Letcher | 300000 | Awaiting action by the State
Fiscal Year 2016 Projects
Project Name | County(s) | Grant Funding | Status
Appalachian Wildlife Center | Bell | 12500000 | ATP Issued
eKAMI Phase I | Johnson | 2500000 | Project Complete
HCTC Utility Training Program | Leslie | 1150000 | Project Complete
Impact Outdoor Adventures Phase I | Clay | 500000 | Project Complete
Marion Branch Industrial Development | Pike | 5000000 | Project Complete
Portal 31 and Other Improvements | Harlan | 2550000 | ATP Issued
Portal 31 Bath House | Harlan | 400000 | Under action by Department
Prestonsburg to David Rails to Trails | Floyd | 1950000 | Project Complete
Royalton Trail Town | Magoffin | 1900000 | ATP Issued
South Fork Elk View Waterline & Campground | Breathitt | 1950000 | Project Complete

## Ohio
Ohio
| Key | Awaiting action by the State
Under action by Department
ATP Issued
Project Complete
Fiscal Year 2021 Projects
Project Name | County(s) | Grant Funding | Status
Jesse Owens State Park | Morgan | 6531250 | Awaiting action by the State
Fiscal Year 2020 Projects
Project Name | County(s) | Grant Funding | Status
Richard Downing Airport | Coshocton | 2117000 | ATP Issued
Cadiz CIC | Harrison | 600000 | ATP Issued
Snow Fork Event Center | Athens | 4200000 | Under Action by the Department
Fiscal Year 2019 Projects
Project Name | County(s) | Grant Funding | Status
Jefferson County Industrial Park | Jefferson | 250000 | ATP Issued
The Wilds - Campground Project | Muskingum | 1004324 | ATP Issued
Buckeye Trail - Black Diamond Trail Network | Perry | 2212640 | Awaiting action by the State
Tecumseh Theater | Perry | 4054974 | Awaiting action by the State
Fiscal Year 2018 Projects
Project Name | County(s) | Grant Funding | Status
The Baileys Trail System | Athens | 1791877 | ATP Issued
Moonville Rail Trail | Vinton & Athens | 1150611 | ATP Issued
Truetown AMD Pigment Production | Athens | 3489408 | ATP Issued
Wellston Recreation Complex | Jackson | 1388027 | ATP Issued
Fiscal Year 2017 Projects
Project Name | County(s) | Grant Funding | Status
Sally Buffalo Park Phase II | Harrison | 631176 | Project Complete
Cadiz Rail High wall | Harrison | 627924 | Project Complete
Powelson Wildlife Area Highwalls - Phase 2 | Muskingum | 4031854 | Project Complete
Friendship Park Highwall | Jefferson | 1205500 | ATP Issued
Laney Field Highwall | Jefferson | 284392 | Project Complete
The Wilds - Trout Lake Dangerous Impoundment | Muskingum | 313788 | Project Complete
D.O. Hall Business Center Mine Stabilization | Guernsey | 1435000 | Project Complete
Beaver Creek State Park | Columbiana | 844269 | ATP Issued

## Pennsylvania
Pennsylvania
| Key | Awaiting action by the State
Under action by Department
ATP Issued
Project Complete
Fiscal Year 2021 Projects
Project Name | County(s) | Grant Funding | Status
Electric Street Development | Lackawanna | 1500000 | ATP Issued
Bethlehem South | Armstrong | 1225000 | ATP Issued
Walkertown | Washington | 1550000 | ATP Issued
Muse | Washington | 1291530 | ATP Issued
Fiscal Year 2020 Projects
Project Name | County(s) | Grant Funding | Status
Walkertown | Washington | 1550000 | ATP Issued
Forks Church North | Armstrong | 420000 | ATP Issued
DL Trail | Luzerne | 941000 | ATP Issued
Audenreid Coal to Solar | Schuylkill | 3950000 | ATP Issued
Tyler Run | Elk | 476000 | Awaiting action by the State
Blacklick Creek Treatment Facility | Indiana | 7000000 | ATP Issued
SGL 332 | Indiana | 3200000 | ATP Issued
Coal Castle Revitilization | Schuylkill | 1500000 | Awaiting action by the State
Mocanaqua AML Recreation Area | Luzerne | 850000 | Awaiting action by the State
Wildcat Run | Clarion | 571000 | Awaiting action by the State
Thompsontown | Clearfield | 1000000 | ATP Issued
Bliss bank 5 | Luzerne | 2721470 | Awaiting action by the State
Belnap South | Armstrong | 350000 | ATP Issued
Muse | Washington | 1291530 | ATP Issued
Fiscal Year 2019 Projects
Project Name | County(s) | Grant Funding | Status
Kerbaugh Road Refuse Pile | Blair | 1000000 | ATP Issued
Tour Ed Mine | Allegheny | 387000 | ATP Issued
Vintondale Refuse Pile Reclamation | Cambria | 487638 | ATP Issued
Quakake Tunnel Treatment Plant | Carbon | 3000000 | ATP Issued
Gladden AMD Active Treatment Plant and Fishing Run Stream Sealing | Allegheny | 3000000 | ATP Issued
Morris Run AMD Treatment Plant | Tioga | 2189522 | ATP Issued
Mine Mitigation, Habitat Restoration, and Educational Trails at Powdermill Nature Reserve | Westmoreland | 1682078 | ATP Issued
Ingleside Northeast | Cambria | 1200000 | ATP Issued
Full Gospel Church | Fayette | 500000 | ATP Issued
Five Mile Hollow | Clinton | 9400000 | ATP Issued
Fiscal Year 2018 Projects
Project Name | County(s) | Grant Funding | Status
Presto-Sygan AMD Remediation at Newbury Marker | Allegheny | 1492000 | ATP Issued
Six Mile Run Restoration | Bedford | 350000 | ATP Issued
Slippery Rock Watershed: AMD Treatment, Education and Recreation Project | Butler | 176246 | ATP Issued
No. 9 Coal Mine and Museum Complex/ Dorrance Colliery | Carbon | 1380000 | ATP Issued
Morgan Run Recreational Facility - West Decatur PO | Clearfield | 309469 | Project Complete
Huling Branch East | Clinton | 3000000 | ATP Issued
Earth Conservancy Bliss Bank 4 | Luzerne | 2500000 | ATP Issued
Anthracite Outdoor Adventure Area (AOAA) / Bear Valley SW | Northumberland | 2500000 | ATP Issued
Anthracite Upland Pointing Dog Association | Schuylkill | 450000 | ATP Issued
Stonycreek Little Conemaugh River Improvement and Reinvestment Project | Somerset and Cambria | 1916000 | ATP Issued
Forest City East - PFBC Access | Susquehanna and Wayne | 1500000 | ATP Issued
Tioga River Restoration/ Morris Run AMD Treatment Plant | Tioga | 4000000 | ATP Issued
Eden East Waterline | Clearfield | 2735754 | ATP Issued
Fiscal Year 2017 Projects
Project Name | County(s) | Grant Funding | Status
Stineman Refuse Pile - Path of the Flood Trail (South Fork Southwest) | Cambria | 2100000 | Project Complete
Quakake Tunnel AMD Treatment - Black Creek Trail | Carbon | 1500000 | ATP Issued
Lackawanna College Subsidence Abatement | Lackawanna | 450000 | Project Complete
Can Do - North Park Drive Business Park | Luzerne | 2000000 | ATP Issued
Hollars Hill South AML - Cranberry Creek Gateway Project | Luzerne | 1929000 | ATP Issued
Earth Conservancy Bliss Bank 3 Business Area | Luzerne | 2500000 | ATP Issued
Swoyersville Refuse Pile - Community Athletic Area | Luzerne | 3350000 | ATP Issued
Porter Floodplain Restoration | Schuylkill | 2000000 | ATP Issued
Donaldson Culm Bank Stream Restoration | Schuylkill | 2000000 | ATP Issued
TASA Refuse Piles - South Sandy Creek Restoration (Venango #1 Pass Through Grant) | Venango | 3156000 | ATP Issued
LHVA Dickson City Trail | Lackawanna | 400000 | ATP Issued
Gladden AMD Active Treatment Plant and Fishing Run Stream Sealing | Allegheny | 3012442 | Project Complete
Fiscal Year 2016 Projects
Project Name | County(s) | Grant Funding | Status
Noblestown Road (Pittsburgh Botanic Gardens) - Phase II | Allegheny | 988500 | Project Complete
Clinton Road (Pittsburgh Airport Innovation Campus) | Allegheny | 500000 | Project Complete
Spaces Corners South/Rayburn Township Joint Municipal Authority Waterline | Armstrong | 608472 | Project Complete
Ehrenfeld Refuse Pile | Cambria | 4870000 | Project Complete
Tresckow South Surface Mine Restoration/Beaver Brook Waterline Extension Project | Carbon & Schuylkill | 4252550 | Project Complete
Pine Grove North (Glen Richey) - Waterline | Clearfield | 4531527 | Project Complete
Fran Contracting Surface Mine Restoration Project (Rock and Camp Run Restoration - Sproul State Forest) | Clinton | 3463993 | Project Complete
Powderly Mine Fire Area Economic Development/Powderly Creek Northeast Underground Mine Fire | Lackawanna | 2000000 | Project Complete
Eckley/Hazleton Rail Trail/Hazel Creek Cleanup | Luzerne | 1983056 | Project Complete
Bowman's Shaft/Pioneer Tunnel | Schuylkill | 205007 | Project Complete
TASA Airfield North (Zelienople Municipal Airport) | Beaver | 2500000 | Project Complete
Potts Run Passive AMD Treatment System (Boardman) | Clearfield | 1508339 | Project Complete
Wingfield Pines Passive AMD Treatment Inflow Reconstruction | Allegheny | 588555 | Project Complete
Cresson Acid Mine Drainage Treatment Plant (SRB low Flow Mine Storage) | Cambria | 2000000 | Project Complete

## Virginia
Virginia
| Key | Awaiting action by the State
Under action by Department
ATP Issued
Project Complete
Fiscal Year 2021 Projects
Project Name | County(s) | Grant Funding | Status
Fiscal Year 2020 Projects
Project Name | County(s) | Grant Funding | Status
Project Intersection Phase IV | City of Norton | 5500000 | ATP Issued
Veldon Dotson Park | Wise | 371000 | Awaiting action by Virginia
Elam Farm Infrastructure | Wise | 1707000 | Awaiting action by Virginia
Breaks Interstate Park Waterpark Expansion | Dickenson | 300000 | Awaiting action by Virginia
Project Innovation | Dickenson | 300000 | Awaiting action by Virginia
Fiscal Year 2019 Projects
Project Name | County(s) | Grant Funding | Status
Project Intersection Phase III | Wise | 1417400 | ATP Issued
Red Onion Industrial Site | Dickenson | 869584 | ATP Issued
Project Thoroughbred | Wise | 2000000 | ATP Issued
Project Thoroughbred Phase II | Wise | 500000 | Awaiting action by Virginia
SR718 Utility Expansion Phase I | Buchanan | 1220016 | Awaiting action by Virginia
Buchanan Tazewell Wirelss Growth Corridor | Buchanan, Tazewell | 1000000 | Awaiting action by Virginia
Russell County IDA Site Infrastructure | Russell | 566000 | Awaiting action by Virginia
Buchanan County Solar Transmission Project | Buchanan | 2000000 | Awaiting action by Virginia
Fiscal Year 2018 Projects
Project Name | County(s) | Grant Funding | Status
Splashdam Waterline Extension | Dickenson | 386500 | Project Complete.
Country Cabin II Facility Improvements | Wise | 82470 | Project Complete.
Wise County IDA - Solar Project Site Prep | Wise | 500000 | ATP Issued
Dante Community Redevelopment | Russell | 269000 | ATP Issued
Project Reclaim Phase II | Russell | 1645704 | Project Complete.
Pocahontas Exhibition Mine and Museum Phase II | Tazewell | 379178 | ATP Issued
Ecotourism in Nature's Wonderland | Buchanan | 2254750 | Awaiting action by Virginia
Project Intersection Phase II | City of Norton | 1782685 | ATP Issued
Enhancing Mountain View Trail System | Wise | 222000 | Awaiting action by Virginia
Trammel Community Revitalization | Dickenson | 150000 | Awaiting action by Virginia.
Fiscal Year 2017 Projects
Project Name | County(s) | Grant Funding | Status
Cranesnest Trail and Portal Closure Project | Dickenson | 711100 | Project Complete
Devil's Fork Loop/Devil's Bathtub | Scott | 283000 | ATP Issued
Project Reclaim | Russell | 3200000 | Project Complete
Project Intersection | City of Norton | 3500000 | ATP Issued
Pocahontas Exhibition Mine and Museum | Tazewell | 1500000 | Project Complete
Real McCoy Cabins | Tazewell | 535000 | ATP Issued
Project Greenhouse | Russell | 19200 | Project Complete* Cancelled by State. Funds expended for NEPA

## West Virginia
Last Updated: 10/26/22
Next Update Due: 11/30/22 | Key | Awaiting action by the State
Under action by Department
ATP Issued
Project Complete
Fiscal Year 2021 Projects
Project Name | County(s) | Grant Funding | Status
Edible Mountain | Ohio | 3234600 | Awaiting action by the State
Middle Ridge Trail System | Kanawha | 300000 | Under action by Department
Appalachain Botanicals Lavendar Farm and Regional Community Center | Fayette | 1600000 | Under action by Department
Meadow River Tiny Home Workshop | Fayette | 420265 | Awaiting action by the State
Stonewood I-79 Development | Taylor | 5000000 | Awaiting action by the State
A.S. Holdings | Raleigh | 4982000 | Under action by Department
McDonald Clan Resort | Logan | 4000000 | Under action by Department
Mylan Park KOA Resort and Campground | Monongalia | 3750000 | Under action by Department
Fiscal Year 2020 Projects
Project Name | County(s) | Grant Funding | Status
Timber Tech Phase 1 | Tucker | 12500000 | Awaiting action by the State
Town of Coalton (Womelsdorff) Water Treatment System Improvements | Randolph | 3325000 | Awaiting action by the State
Meadow River Rail Trail | Greenbrier and Fayette | 1850408 | Awaiting action by the State
Stonewall Resort Historic Water Trail, Roanoke Event Center, and Related Amenities | Lewis County | 1629592 | Awaiting action by the State
Rising Estates Trail Lodging Project | Logan | 1995000 | Awaiting action by the State
Eastern Wyoming PSD Water Treatment Plant Upgrade | Wyoming | 2200000 | Awaiting action by the State
Fiscal Year 2019 Projects
Project Name | County(s) | Grant Funding | Status
Harper-Eccles Sewer Extension | Raleigh | 7647398 | Awaiting action by the State
Rhodell Water Service Upgrade | Raleigh | 2125000 | Awaiting action by the State
Claudia L. Workman Wildlife Center | Kanawha | 959613 | ATP Issued
Blackwater River Loop Project: Hiking, Biking, and Heritage Tourism | Tucker | 818000 | Awaiting action by the State
RECREATING | Preston | 1000000 | ATP Issued
Fleming- An Old Mining Town Transformation to Rustic Ravines | Wayne | 250000 | ATP Issued
Brenton/Baileysville Waterline Extension | Wyoming | 4500000 | ATP Issued
Indian Creek ATV Resort | Boone | 3263000 | Awaiting action by the State
Twin Hollow Campground and Cabins Expansion | Mingo | 2669422 | Awaiting action by the State
Leon Street Slip Remediation | Harrison | 1293165 | Project Complete
Fiscal Year 2018 Projects
Project Name | County(s) | Grant Funding | Status
RE-CREATE | Preston | 3014000 | ATP Issued
Town of Bradshaw Sanitary Sewer Upgrade | McDowell | 1500000 | ATP Issued
Iaeger Regional Sewer Project - Phase 1 | McDowell | 1000000 | ATP Issued
McDowell PSD Ashland/Crumpler (Elkhorn Creek) | McDowell | 4115000 | ATP Issued
West Virginia Elk Restoration Project Visitor Center | Logan, Mingo | 1550000 | ATP Issued
Ashland Resort Tourism Development Park | McDowell | 2278500 | ATP Issued
Berwind Water Treatment Plant | McDowell | 238000 | ATP Issued
Ivy Branch Off Road Development Park Phase 2 | Boone | 1300000 | ATP Issued
Vandalia: Highlands Conservation and Recreation | Tucker | 400000 | Project Complete
Patriot Guardens Apple Production Project | Clay, Nicholas, Webster | 5000000 | ATP Issued
Renaissance Village | McDowell | 1000000 | Project Complete
Oak Hill Sanitary Board- Minden Sanitary Sewer System Rehabilitation | Fayette | 1500000 | Awaiting action by the State
White Oak Waterline Extension | Raleigh | 1800000 | ATP Issued
Fiscal Year 2017 Projects
Project Name | County(s) | Grant Funding | Status
ATV TrailCamp at Coaldale | Mercer | 1800000 | ATP Issued
Beaver Creek Fishery Enhancement | Tucker | 295700 | ATP Issued
Clear Fork Rail Trail | Raleigh | 2250000 | ATP Issued
Grace Chapel Remediation and Redevelopment | Preston | 2208102 | ATP Issued
Ivy Branch Off Road Development Project Phase I | Lincoln, Boone | 3164478.29 | Project Complete
Triadelphia ATV Resort Project | Logan | 1725521.71 | ATP Issued
Livestock, Processing and Value-Added Facility | Kanawha | 5875000 | Project Complete
Northern Cardinal Farms Price-Hunter Branch Hatfield AML | Boone | 837113.23 | Project Complete* Cancelled by West Virginia
Mountain State Broadband Expressway Phase II | Various | 3350000 | Awaiting action by the state
MCPARC Community Recreation and Wellness Complex | Marion | 1500000 | Awaiting action by the state
Middletown Commons Redevelopment Project | Marion | 1500000 | ATP Issued
Fiscal Year 2016 Projects
Project Name | County(s) | Grant Funding | Status
Aquaponics on AML: Fish, Vegetables, Renewables, and Mine Air/Water | Mingo | 3581989 | ATP Issued
Patriot Guardens Golden Delicious Apple Project/Patriot Guardens AML Project Werth Highwalls & Spoil | Clay, Nicholas, Webster | 5295000 | Project Complete
Danese PSD Crickmer Road Waterline Extension | Fayette | 944208 | Project Complete
Danese PSD Highland Mountain Waterline Extension | Fayette | 2629711 | Project Complete
Mountain State Broadband Expressway | Various | 12526081 | ATP Issued
WV Elk Restoration Project | Logan, Mingo | 1029011 | ATP Issued
I-79 Technology Park Mine Reclamation and Economic Expansion | Marion | 3994000 | Project Complete

## Alabama
Alabama
| Key | Awaiting action by the State
Under action by Department
ATP Issued
Project Complete
Fiscal Year 2021 Projects
Project Name | County(s) | Grant Funding | Status
West Blocton Coke Ovens Project | Bibb | 2469700 | Under action by Department
The Hubb at Grants Mill Project | Jefferson | 7530300 | Under action by Department
Fiscal Year 2020 Projects
Project Name | County(s) | Grant Funding | Status
North Fork Creek | Tuscaloosa | 3427426 | Awaiting action by the State
Hillsboro Sports Park | Shelby | 5000000 | Awaiting action by the State
Fiscal Year 2019 Projects
Project Name | County(s) | Grant Funding | Status
Walker County Agricultural Restoration | Walker | 600000 | Awaiting action by the State
Connected Jasper - Alabama Power | Walker | 1640000 | ATP Issued
Historic West Blocton | Bibb | 2864240 | Awaiting action by the State
Eagle Cove Marina | Tuscaloosa | 3895760 | Awaiting action by the State
Fiscal Year 2018 Projects
Project Name | County(s) | Grant Funding | Status
Sicard Hollow Dog Park - City of Vesatavia | Jefferson | 300000 | ATP Issued
Piper Mine Reclamation - US Fish & Wildlife | Bibb | 2500000 | ATP Issued
U.S I-22 - Exit 78 Project - Drummond Company | Walker | 3000000 | ATP Issued
Grand River Parcel 15 - US Steel | Jefferson | 2200000 | Awaiting action by the State
Pine Ridge - Drummond Co - City of Vestavia | Jefferson | 2000000 | Awaiting action by the State
Fiscal Year 2017 Projects
Project Name | County(s) | Grant Funding | Status
Sicard Hollow Athletic Complex - City of Vestvia | Jefferson | 750000 | Project Complete
Grand River Technology Park - US Steel | Jefferson | 6000000 | Project Complete
Hillsboro Community - US Steel | Shelby | 3250000 | Project Complete

## Tribes
Navajo Nation, Hopi Tribe, and Crow Tribe
| Key | Awaiting action by the Tribe
Under action by Department
ATP Issued
Project Complete
Fiscal Year 2019 Projects
Project Name | Tribe | Grant Funding | Status
Shonto Hotel - HVAC System | Navajo | 333333333 | ATP Issued
Crow Tribe Waste Reduction and Recycling Project - Phase 2 | Crow | 333333333 | Awaiting action by the Tribe
Fiscal Year 2018 Projects
Project Name | Tribe | Grant Funding | Status
Kayenta Industrial park | Navajo | 333333333 | ATP Issued
Crow Tribe Waste Reduction and Recycling Project | Crow | 333333333 | Awaiting action by the Tribe
Water and Infrastructure Pilot Project | Hopi | 333333333 | Awaiting action by the Tribe